C100 SYSTEM

Collegiate 100 Performance & Development Platform

────────────────────────────────────────

IMPLEMENTATION ROADMAP

Phased Plan from Planning to National Scale

Document 8 of 8  |  Version 1.0  |  Confidential

# 8. Implementation Roadmap

This document defines the phased plan for building, testing, and scaling the C100 System. Each phase has clear objectives, deliverables, and success criteria.

## Phase 1 — Planning & Design

### Duration: 4–6 Weeks

Objective: Define everything before writing a single line of code. Complete all system documentation and design specifications.

| Deliverable | Description |
| --- | --- |
| System Documentation | Complete all 8 documents in the C100 System document set |
| Stakeholder Review | Review system design with FVSU Chapter President, Executive Board, and 100 Black Men of Macon-Middle Georgia liaison |
| Committee Structure Finalization | Confirm committee assignments, chair designations, and bylaws chair role |
| Wireframes / Mockups | Design all primary screens: login, dashboard, events, QR check-in, committee leaderboard |
| Technical Architecture | Select technology stack, hosting provider, database, and email delivery service |
| Data Model Validation | Confirm all 6 data models meet operational requirements |
| Security Review | Define authentication approach, session management, and data privacy requirements |
| Project Plan | Build sprint-by-sprint development schedule for Phase 2 |

Phase 1 Success Criteria All 8 system documents completed and approved. Technical stack selected. Wireframes reviewed and approved by Executive Board. Development team (or developer) identified and under agreement.

## Phase 2 — MVP Build

### Duration: 8–12 Weeks

Objective: Build the full MVP as defined in Document 7. Deliver a working, tested system ready for chapter use.

| Sprint | Focus |
| --- | --- |
| Sprint 1 (Weeks 1–2) | Authentication system: registration, email verification, login, roles, password reset, admin panel basics |
| Sprint 2 (Weeks 3–4) | Committee system: committee creation, member assignment, committee profiles, private roster view |
| Sprint 3 (Weeks 5–6) | Event system: event creation, event listing, event management, event history |
| Sprint 4 (Weeks 7–8) | QR Attendance system: dynamic QR generation, 60-second rotation, member scan check-in, time window, duplicate prevention |
| Sprint 5 (Weeks 9–10) | Dashboard build: member dashboard, chair dashboard, E-Board dashboard, admin panel completion |
| Sprint 6 (Weeks 11–12) | Nudge system: weekly check logic, tier assignment, email nudges, in-app notifications, nudge log |

After each sprint:

- Internal code review and testing

- Demo to chapter President or designated stakeholder

- Bug fixes before moving to next sprint

Phase 2 Success Criteria All MVP features (Document 7) built and passing internal testing. Admin can create an event, display a QR code, and verify that member check-in records correctly. Nudge system sends correct email for each tier. No critical bugs in any core flow.

## Phase 3 — Pilot Testing with FVSU Chapter

### Duration: One Full Semester (Approximately 16 Weeks)

Objective: Run the C100 System live with the full FVSU Trailblazing Chapter. Identify real-world gaps, errors, and improvement opportunities.

| Timeline | Activity |
| --- | --- |
| Week 1–2 | Onboard all chapter members — accounts created, committees assigned, roles set |
| Week 3 | Training session for all members: how to use the dashboard and QR check-in |
| Week 3 | Training session for committee chairs: event creation, QR activation, dashboard monitoring |
| Weeks 3–14 | Live semester operation — all events use QR attendance, nudges run automatically |
| Week 8 | Mid-semester data review with Executive Board — assess engagement trends, catch issues |
| Week 15 | End-of-semester review: run award selection process using system data |
| Week 15 | Awards announced at chapter end-of-semester event |
| Week 16 | Post-semester retrospective: collect feedback from members, chairs, and E-Board |

Feedback collection methods:

- Anonymous member survey at Week 8 and Week 16

- Chair debrief interviews at end of semester

- E-Board structured review session using system data

Phase 3 Success Criteria 75%+ of members used the system for QR check-in at least once. Nudge system correctly identified and messaged all at-risk members. End-of-semester awards selected using system data. Executive Board confirms the system is more efficient than previous manual tracking. At least 3 documented areas for improvement identified.

## Phase 4 — Iteration & Expansion

### Duration: 8–12 Weeks (Following Pilot Semester)

Objective: Address all issues identified in Phase 3. Add Version 2 features based on validated needs.

Priority fixes and additions based on expected Phase 3 learnings:

| Item | Description |
| --- | --- |
| Bug Fixes | Address all critical and high-priority bugs identified during pilot |
| UX Improvements | Simplify flows that caused member confusion during onboarding |
| SMS Nudges | Add SMS delivery channel for nudge messages |
| Task Self-Reporting | Build member-facing task submission flow with chair approval workflow |
| Impact Score Display | Add impact vs. activity breakdown to member dashboard |
| Export Reports | Allow E-Board to export semester performance data as PDF or CSV |
| Bylaws Reference Module | Build Bylaws Chair tool: searchable bylaws reference, amendment proposal drafting |
| Conference Eligibility Report | Automated report generation for conference selection process |

Phase 4 Success Criteria All critical Phase 3 bugs resolved. SMS nudges operational. Task submission flow live and tested. Export reports functional. System ready for replication to a second chapter.

## Phase 5 — Scaling to Additional Chapters

### Duration: Ongoing — Beginning After Phase 4 Completion

Objective: Package and deploy the C100 System for adoption by other Collegiate 100 chapters across the 100 Black Men of America network.

| Feature | Description |
| --- | --- |
| Multi-Chapter Architecture | Rebuild admin layer to support isolated chapter environments under one platform |
| Chapter Onboarding Package | Create a standardized onboarding guide, training materials, and setup checklist for new chapters |
| National Admin Dashboard | Build a super-admin view for 100 Black Men of America, Inc. to view cross-chapter engagement data |
| Chapter Customization | Allow chapters to configure: committee names, event types, point values, semester dates |
| Cross-Chapter Benchmarking | Anonymous comparison of chapter performance metrics across the national network |
| Scholarship Fund Integration | Connect scholarship award process to fund management system |
| Alumni Pipeline Tracking | Begin tracking members post-graduation toward full 100 Black Men of America membership |
| API Documentation | Publish API documentation for potential third-party integrations |

Phase 5 Success Criteria At least 3 Collegiate 100 chapters using the system in a live semester. National admin dashboard operational. Chapter onboarding process completed in under 2 weeks per chapter. System stable under multi-chapter load.

## 8.1 Summary Timeline

| Phase | Duration & Success Criteria |
| --- | --- |
| Phase 1 — Planning & Design | 4–6 weeks ¦ All documents complete, stack selected, wireframes approved |
| Phase 2 — MVP Build | 8–12 weeks ¦ Fully functional MVP delivered and tested |
| Phase 3 — Pilot (FVSU) | 16 weeks (one semester) ¦ Live chapter operation, data collected, awards run |
| Phase 4 — Iteration | 8–12 weeks ¦ Bugs fixed, V2 features added, ready to replicate |
| Phase 5 — Scale | Ongoing ¦ Additional chapters onboarded, national dashboard live |

Total estimated time from start of planning to end of first live semester: approximately 9–12 months.

Final Note The C100 System is not a tool built for its own sake. It is a performance infrastructure built to serve the mission of the 100 Black Men of America — mentoring youth, advancing education, developing economic opportunity, and building healthy communities. Every feature, every data point, and every nudge is in service of that mission.